## Sheet1
Client feedback | Original scope reference | Current code / app evidence | Classification
Replace logo, rename CRM to FYX, change login wording | No branding specification in the XLSX | client/src/pages/Login.tsx still renders “Interiors by DeX” and “CRM Platform, Sign in.” | Change request / feature creep
CRM logs out after 15–20 minutes while in use | No explicit session-duration requirement | server/src/routes/auth.ts returns a refresh token, but client/src/pages/Login.tsx saves only crm_token; client/src/lib/api.ts logs the user out on a 401 and never refreshes the session. | Confirmed defect
Rename the gate prompt to FYX wording | Scope requires stage movement/gates, not copywriting | No FYX terminology exists in current gate UI/configuration. | Change request / feature creep
On Hold and Inactive should use the same portal format as Active | XLSX 2.4–2.6: list view, Inactive and On Hold states | Current Pipeline.tsx treats status separately from stages and has Active/On Hold/Inactive tabs. | Already addressed in current source
Show unread/new lead count | Dashboard requires totals by period, not unread counters | No original requirement for unopened/unread lead counting. | Change request / feature creep
Lead-tab filters must match Sales Pipeline; add Expected OB Date; change filter flow/headings | XLSX 2.7, 2.8 and report filtering 14.14 | Current LeadList.tsx and Pipeline.tsx both send the key filter parameters; Expected OB Date is present in LeadList.tsx, and the backend parses it in server/src/routes/leads.ts. Exact visual parity/headings need browser verification. | Already addressed in current source for core filters; SOW bug candidate, reproduce for visual headings/layout
Replace Designer filter with Lead Origin Date | XLSX 2.7 explicitly requires Designer filtering and date-range filtering | Removing Designer would reduce a specified original filter. | Scope conflict
Date-wise notification feed for calls, meetings, tasks, SLA breaches | XLSX 3.4–3.6, 9.1–9.7 | NotificationList.tsx groups notifications by day; overdue-task notifications are scheduled in midnightOverdueTask.ts. Event-by-event coverage needs testing. | SOW bug candidate, reproduce
Remove Intent Rating and replace it with stage-days/TAT/budget table | XLSX 1.7 explicitly requires High/Medium/Low intent | Intent remains stored/filterable in the source. TAT/SLA reporting is adjacent scope, but replacing intent is not. | Scope conflict for removing intent; change request for the new table
Intent should auto-update at every stage movement | XLSX 1.7 requires intent, but does not prescribe an automatic stage-scoring engine | Current intent scoring is based on meeting information, not a defined stage-by-stage rule. | Change request / feature creep
Latest quote is not reflected in Lead Details | XLSX 5.3 and 5.5 require quote activity and lead-level quote visibility | LeadDetail.tsx fetches quotes from /quotes/lead/:leadId; sorting/refresh behavior must be tested with an actual latest quote. | SOW bug candidate, reproduce
Country-specific phone-code and digit validation | XLSX requires phone capture, not country-specific validation | No international validation rules were promised. | Change request / feature creep
Rename Move-in/Possession Date to Expected Interiors Handover Date | XLSX 1.6 requires possession timeline | Same business concept, but exact label was not specified. | Change request
Permit skips of DQL, PR and PD, while retaining skipped-stage requirements | Original scope describes a pipeline but does not explicitly define skipping | Current stageRequirements.ts and leads.ts explicitly allow DQL, Proposal Ready and Proposal Discussion skipping and accumulate the appropriate requirements. | Already addressed in current source
PP → OB cannot progress because the PD file/checklist is not available | No specific PD-file-folder design in original SOW | Current stage requirement code handles Proposal Discussion skip rules; actual file visibility must be tested in the browser. | SOW bug candidate, reproduce for the current UI; file-folder design itself is later scope
OB checklist meeting does not appear in Meetings tab | XLSX 4.1–4.8 requires meeting scheduling, statuses and MOM workflow | Current app has dedicated meetings and OB/OBM checklist components, but the cross-tab refresh/sync must be reproduced. | SOW bug candidate, reproduce
OB checklist only updates after a full refresh | Checklists are not a named original-SOW module; meeting workflow is | Current code has checklist components and API-driven state. Live-refresh behavior cannot be proven statically. | Later-module bug candidate, reproduce
OB → OBM must require client-confirmation checkbox; remove generated quote gate | OBM stage and exact gate rules are not defined in original scope | Current stage rules and checklist logic exist, but this is a new gate policy beyond the XLSX. | Change request / feature creep
Welcome-mail attachment is missing | XLSX requires onboarding email and email preview; it does not specify a welcome-mail attachment | Attachment requirement is not an original deliverable. | Change request; current mail behavior should still be tested separately
OBM → DIP requires mail-approval screenshot; DIP checklist items changed | XLSX comments mention post-onboarding controls and NPS before DIP, but not screenshots or this detailed checklist | Current source has DIP/OBM checklist gates. Screenshot evidence and exact checklist policy are later additions. | Partial scope change
Cannot move to DIP after completing current gates | XLSX comments make DIP/post-onboarding completion part of the expected process | Current server contains explicit OBM → DIP gate logic. The reported block must be reproduced against current data. | SOW bug candidate, reproduce
Add project team members; BL approval; one primary designer | XLSX covers lead assignment and roles, not project-team membership or primary-designer modeling | TeamTab.tsx now exists, so the PDF likely predates later work; primary-designer policy still needs checking. | Change request, with some later implementation already present
Show Client NPS next to lead; distinguish NPS from intent | XLSX comments mention NPS after onboarding, but not an NPS display system | Current lead API exposes NPS-related data; exact display/score design exceeds scope. | Partial scope change
Roadmap text is cut off | XLSX 2.1–2.3 requires a usable visual pipeline | Client PDF is evidence of a UI issue, but current responsive UI needs verification. | SOW bug candidate, reproduce
One latest-first unified activity feed with actor and timestamp | XLSX 11.1–11.3 explicitly requires automatic timeline, actor and timestamp | Current Lead Detail has an Activity tab; exact ordering and whether all activities are unified need a current browser test. | SOW bug candidate, reproduce
Add a chat box for internal notes | XLSX 1.8 requires free-text notes, not chat | A real-time chat interaction is beyond plain notes. | Change request / feature creep
Add Schedule Call: date/time, type, agenda and notification choice | XLSX 3.1–3.6 requires call logging, callback date/time, and reminders | Current CallLogTab.tsx and calls routes exist. Internal/external notification choice and every requested field need verification. | SOW bug candidate, reproduce for call basics; change request for global notification controls
Internal Notes / External Notes; only external notes sent to client | XLSX requires notes and client communications, not two-channel note architecture | This is a new data and communication model. | Change request / feature creep
Remove Follow-up Task completely | XLSX 3.4 explicitly says a follow-up task after every call is mandatory | This would remove an agreed feature. | Scope conflict
Rename Follow-up Task; change counter; show completed/scheduled/rescheduled/no-show totals | Original scope requires follow-up tracking but not these labels/counters | FollowUpTab.tsx currently shows pending and overdue counts. Requested reporting presentation is additional. | Change request
Task attachment only at completion, not creation | No original attachment rule for tasks | Current FollowUpTab.tsx permits task creation without attachments and supports multiple files. | Already addressed in current source
Assign task to another team member | XLSX requires manager visibility, not arbitrary task reassignment | Current task model supports assignees, but this exact workflow is not in scope. | Change request
Reschedule task with date/time/agenda; rename Outcome to Reason | XLSX requires follow-up reminders, not this complete rescheduling UX | Current task routes support rescheduling and preserve agenda/history. Exact UI requirements are added scope. | Partly addressed; change request for presentation details
Block all lead activity until an overdue task is rescheduled/cancelled | XLSX requires overdue notification/manager view, not a global activity lock | This is a major new business-control rule. | Change request / feature creep
Newly created task not shown in activity feed | XLSX 11.1 says every action should be logged; task activity is a reasonable extension | Current task routes create activity entries, but live feed refresh must be tested. | SOW bug candidate, reproduce
Rename PD to Pitch Discussion | XLSX does not prescribe this exact label | This is terminology/copy change. | Change request
Restrict attachment categories; attach to email | Original scope does not define broad attachment category/file-management rules | Later file-management enhancement. | Change request / feature creep
Meeting mode/location dropdown missing | XLSX 4.3 explicitly requires meeting modes; comments include office/site/virtual/public-place context | Current Meetings tab contains mode/location support, but exact UI/state needs test. | SOW bug candidate, reproduce
Floor plans uploaded at EL/MQL/DQL do not appear in Files tab | Original scope does not define a central Files tab or floor-plan synchronization | Current server has floor-plan upload plus stage file handling. Sync behavior is a later-feature defect candidate, not original-SOW breach. | Later-module bug candidate, reproduce
Allow multiple attachments in all tabs | Original scope does not define an all-tabs attachment system | Current Calls, Meetings and Tasks components support multi-file state. Other tabs require verification. | Change request, partly already implemented
Direct Mark Inactive from On Hold; inactivity reasons and typed notes | XLSX 2.5–2.6 requires inactive reason and On Hold with revival date | LeadDetail.tsx and leads.ts provide a direct status path and mandatory inactive reason. Exact reason taxonomy/notes are new. | Already addressed for direct action; change request for taxonomy/details
Mandatory email/SMS on inactivity and reactivation | XLSX comments request auto email/SMS for inactivation; reactivation messaging is not specified | API supports client notification controls; whether delivery occurs needs integration testing. | SOW bug candidate, reproduce for inactivation; change request for reactivation policy
Quote builder must only open the representative’s PID quote | XLSX requires designers only edit their assigned leads and quote-builder access | This is a legitimate authorization concern, but cross-system PID enforcement is not detailed in scope. | SOW-related security bug candidate, reproduce
Auto-fill PID, name and project details in quote builder | XLSX 5.2 explicitly requires Lead ID prefill | PID/Lead ID is in scope; name and project details extend it. | Partial scope change
Global Internal/External notification checkbox everywhere | XLSX specifies particular email/WhatsApp automations, not a global delivery policy | New communication-control framework. | Change request / feature creep
Designer edits every email before client send | XLSX 8.4 allows preview and editing for selected email types | “Every email” is broader than the agreed requirement. | Change request beyond existing preview requirement
Management edits all email templates | No admin-template editor in original scope | Existing admin mail-template work is a later enhancement. | Change request / feature creep
Tuesday/week-start/day-start/one-hour task and meeting reminders | XLSX requires due reminders and manager views, but not this schedule | Server currently runs overdue-task processing; exact reminder timings are not implemented by the shown job. | Partial scope change
Proposal Ready email should omit attachment; other mail attachment rules | Original scope requires automated emails, not this attachment matrix | New mail-policy decision. | Change request
Use calendar and clock controls instead of manual date/time | Scope requires scheduled dates/times, not a specific control type | Current UI already uses date/time inputs in several areas; broad consistency request is additional UI scope. | Change request
Sales incentive only after DIP | XLSX comments say sales work closes after post-onboarding/DIP; no incentive-calculation engine is specified | Incentive dashboards are later product scope. | Change request / feature creep
Designer-created leads should not enter MQL without project details | XLSX requires project details, but does not define the exact MQL-entry gate | Current stage rules intentionally start new leads at MQL. This needs a business-rule decision, not an assumed defect label. | Partial scope change
Expected OB Date reminder email/message | No Expected OB reminder requirement in XLSX | New automation requirement. | Change request / feature creep
Dashboard card titles, KPI logic and clickable drill-downs | XLSX 13.1–13.6 requires dashboard totals, funnel, SLA panel and activity; no specific card names/drilldowns | Current Dashboard.tsx contains funnel, conversion and some linked scopes. Exact new cards and click-through behavior need testing. | Partial scope change
Separate Sales/Design performance scores; metrics; medals | XLSX requires Designer and BL performance reports, not named scores, medals or formulas | New analytics/gamification design. | Change request / feature creep
BL/BH project flag | XLSX requires SLA badges/alerts, not manual project flagging | Current dashboard references flagged projects, but manual BL/BH flag authority is a later feature. | Change request
Remove NPS forecast; booking forecast from Expected OB Date | Forecasting is not listed in original dashboard/report scope | New analytics rules. | Change request / feature creep
Calendar views for tasks/calls/meetings; wrong date/time display | XLSX requires dated calls/meetings/tasks and reminders | Current app has scheduling data; a dedicated personal-calendar UX is beyond the SOW. Wrong displayed dates need reproduction. | SOW bug candidate, reproduce for incorrect dates; change request for calendar UX
Inactivate a lead should cancel/null all pending tasks | No task-cancellation rule in original scope | New lifecycle automation. | Change request / feature creep
Funnel calculation must use Total Leads Received as denominator | XLSX 13.4 requires conversion rates, but does not define the formula | The PDF screenshot showing a 200% stage “conversion” is a strong sign of a metric defect. The client’s precise replacement formula is a new reporting-rule decision. | SOW bug candidate, reproduce for invalid calculation; change request for exact formula